## Summary
Self Storage Construction Cost Summary
Calculated from entered fictional budget and cost records; warnings require human review.
Portfolio Indicator | Calculated Value |  | Contractor | Committed | Paid | Unpaid Committed
Total Budget
Committed
Paid
Unpaid Committed
Remaining Budget
Committed Percentage
Past-Due Cost Items
Rows Flagged
Budget Line | Budget | Committed | Paid

## Cost Tracker
Self Storage Construction Cost Tracker
Track fictional commitments, change orders, payment requests, draws, due dates, and owners.
Approved or paid commitments count as committed; only paid Payment entries count as paid. Warnings request human review.
Entry ID | Facility | Budget Line | Contractor | Draw / Change Order Ref | Cost Type | Period | Amount | Owner | Status | Due Date | Notes | Committed Amount | Paid Amount | Review Flag
CST-001 | Fictional Cedar Ridge Storage | Site Work | Fictional Granite Path Civil LLC | Contract GC-01 | Original Commitment | 2026-09-01 | 360000 | Fictional Employee Avery Brooks | Approved | 2026-09-21 | Fictional grading and drainage commitment.
CST-002 | Fictional Cedar Ridge Storage | Site Work | Fictional Granite Path Civil LLC | Draw 01 | Payment | 2026-08-01 | 120000 | Fictional Employee Avery Brooks | Paid | 2026-08-27 | Fictional completed earthwork draw.
CST-003 | Fictional Cedar Ridge Storage | Site Work | Fictional Granite Path Civil LLC | CO-01 | Change Order | 2026-09-01 | 28000 | Fictional Employee Avery Brooks | Approved | 2026-10-01 | Fictional additional soil removal.
CST-004 | Fictional Cedar Ridge Storage | Foundations | Fictional Bright Beam Concrete Co. | Contract FC-01 | Original Commitment | 2026-09-01 | 540000 | Fictional Employee Avery Brooks | Approved | 2026-10-11 | Fictional slab and footing commitment.
CST-005 | Fictional Cedar Ridge Storage | Foundations | Fictional Bright Beam Concrete Co. | Draw 01 | Payment | 2026-09-01 | 160000 | Fictional Employee Morgan Reed | Submitted | 2026-09-06 | Fictional payment request awaiting internal review.
CST-006 | Fictional Cedar Ridge Storage | Structural Steel | Fictional Highline Frame Works | Contract SS-01 | Original Commitment | 2026-09-01 | 790000 | Fictional Employee Morgan Reed | Approved | 2026-10-26 | Fictional structural framing commitment.
CST-007 | Fictional Bluebird Avenue Storage | Building Envelope | Fictional Harbor Shield Exteriors | Contract BE-01 | Original Commitment | 2026-09-01 | 710000 | Fictional Employee Morgan Reed | Approved | 2026-10-06 | Fictional roofing and wall system commitment.
CST-008 | Fictional Bluebird Avenue Storage | Building Envelope | Fictional Harbor Shield Exteriors | Draw 01 | Payment | 2026-08-01 | 210000 | Fictional Employee Morgan Reed | Paid | 2026-09-01 | Fictional paid exterior materials draw.
CST-009 | Fictional Bluebird Avenue Storage | Climate Systems | Fictional CoolCurrent Mechanical | CO-02 | Change Order | 2026-09-01 | 35000 | Fictional Employee Jordan Lee | Draft | 2026-10-16 | Fictional draft equipment revision.
CST-010 | Fictional Summit Box Storage | Site Work | Fictional Granite Path Civil LLC | Contract GC-02 | Original Commitment | 2026-09-01 | 405000 | Fictional Employee Avery Brooks | Approved | 2026-09-29 | Fictional site package submitted above the entered budget.

## Budget Lines
Self Storage Construction Budget Lines
Enter one budget row for each fictional facility and budget line combination.
Yellow cells are editable. Calculated committed and paid amounts come from Cost Tracker entries.
Budget ID | Facility | Budget Line | Budget Amount | Owner | Notes | Committed Amount | Paid Amount | Unpaid Committed | Remaining Budget | Committed Percentage | Review Status
BUD-001 | Fictional Cedar Ridge Storage | Site Work | 420000 | Fictional Employee Avery Brooks | Initial fictional site package.
BUD-002 | Fictional Cedar Ridge Storage | Foundations | 590000 | Fictional Employee Avery Brooks | Foundation allowance for the fictional project.
BUD-003 | Fictional Cedar Ridge Storage | Structural Steel | 840000 | Fictional Employee Morgan Reed | Steel framing budget.
BUD-004 | Fictional Cedar Ridge Storage | Electrical | 310000 | Fictional Employee Jordan Lee | Electrical distribution budget.
BUD-005 | Fictional Bluebird Avenue Storage | Building Envelope | 760000 | Fictional Employee Morgan Reed | Roofing and exterior wall budget.
BUD-006 | Fictional Bluebird Avenue Storage | Climate Systems | 480000 | Fictional Employee Jordan Lee | Climate system budget.
BUD-007 | Fictional Bluebird Avenue Storage | Security and Access | 120000 | Fictional Employee Casey North | Fictional access equipment budget.
BUD-008 | Fictional Bluebird Avenue Storage | General Conditions | 260000 | Fictional Employee Casey North | General conditions budget.
BUD-009 | Fictional Summit Box Storage | Site Work | 390000 | Fictional Employee Avery Brooks | Early site work budget.
BUD-010 | Fictional Summit Box Storage | Foundations | 550000 | Fictional Employee Morgan Reed | Foundation construction budget.

## Assumptions
Construction Cost Tracker Assumptions
Edit the yellow option lists and control values before using the working sheets.
Facility Options | Budget Line Options | Contractor Options | Cost Type Options | Status Options | Owner Options | Control | Editable Value | Purpose
Fictional Cedar Ridge Storage | Site Work | Fictional Granite Path Civil LLC | Original Commitment | Draft | Fictional Employee Avery Brooks | Budget review threshold | 90% | Marks a budget line Near budget at or above this committed percentage.
Fictional Bluebird Avenue Storage | Foundations | Fictional Bright Beam Concrete Co. | Change Order | Approved | Fictional Employee Morgan Reed | Earliest entry date | 2021-01-01 | Lower date limit for periods and due dates.
Fictional Summit Box Storage | Structural Steel | Fictional Highline Frame Works | Payment | Submitted | Fictional Employee Jordan Lee | Latest entry date | 2036-12-31 | Upper date limit for periods and due dates.
| Building Envelope | Fictional Harbor Shield Exteriors |  | Paid | Fictional Employee Casey North | Maximum single amount | 100000000 | Upper amount limit for one budget or cost entry.
| Electrical | Fictional Copper Trail Electric |  | On Hold
| Climate Systems | Fictional CoolCurrent Mechanical |  | Void
| Security and Access | Fictional SafeLane Systems
| General Conditions | Fictional Fieldstone Builders