## Summary
Self Storage Development Budget Summary
Calculated from Budget entries as of 09/11/2026. Review flags are planning prompts for human review.
Total Budget |  | Total Forecast |  | Total Drawn |  | Budget Remaining
Forecast Rate |  | Draw Rate |  | Open Items |  | Review Items
Earliest Due Date |  | Latest Due Date |  | Forecast Variance |  | Budget Lines
Budget by Category
Category | Budget | Forecast | Drawn | Variance | Draw Rate | Lines | Review Items
Budget by Draw Period
Draw Period | Budget | Forecast | Drawn | Variance | Draw Rate | Lines

## Budget
Self Storage Development Budget
Enter planning amounts in yellow cells. Formula columns calculate unit cost, remaining budget, and human review flags.
Prepared for 100 budget lines; 10 fictional examples are included.
Facility | Budget Category | Cost Item | Quantity | Unit | Draw Period | Budget Amount | Forecast Amount | Drawn Amount | Budget per Unit | Owner | Status | Due Date | Budget Remaining | Review Flag | Notes
Juniper Lantern Storage at Mesa Vista (Fictional) | Land | Land planning allowance | 1 | lump sum | Predevelopment | 4200000 | 4150000 | 4150000 |  | Fictional Development Lead | Complete | 2026-05-14 |  |  | Fictional planning allowance; verify project scope.
Juniper Lantern Storage at Mesa Vista (Fictional) | Design | Architectural design allowance | 1 | lump sum | Predevelopment | 650000 | 620000 | 410000 |  | Fictional Design Team | In Progress | 2026-10-11 |  |  | Concept and drawing allowance for the fictional facility.
Juniper Lantern Storage at Mesa Vista (Fictional) | Permits & Fees | Local review and permit allowance | 1 | lump sum | Draw 1 | 310000 | 290000 | 150000 |  | Fictional Project Manager | In Progress | 2026-08-27 |  |  | Schedule assumption requires human review.
Juniper Lantern Storage at Mesa Vista (Fictional) | Site Work | Grading and utility allowance | 235000 | square feet | Draw 2 | 2400000 | 2250000 | 1200000 |  | Fictional Site Lead | In Progress | 2026-11-10 |  |  | Quantity is a fictional planning basis.
Juniper Lantern Storage at Mesa Vista (Fictional) | Structures | Storage building package allowance | 840 | units | Draw 3 | 6800000 | 6500000 | 2700000 |  | Fictional Development Lead | Scheduled | 2027-01-09 |  |  | Large line is intentionally included for threshold review.
Juniper Lantern Storage at Mesa Vista (Fictional) | Security Systems | Camera and access equipment allowance | 72 | units | Draw 4 | 420000 | 435000 | 400000 |  | Fictional Site Lead | In Progress | 2027-02-08 |  |  | Forecast is intentionally above budget for testing.
Juniper Lantern Storage at Mesa Vista (Fictional) | Contingency | Project contingency reserve | 1 | lump sum | Draw 5 | 1150000 |  |  |  | Fictional Finance Review | Planned | 2027-04-09 |  |  | Editable reserve assumption; no outcome is guaranteed.
Juniper Lantern Storage at Mesa Vista (Fictional) | Other | Office and leasing area fit-out | 1 | lump sum | Draw 5 | 280000 | 240000 |  |  | Fictional Project Manager | Quoted | 2027-05-09 |  |  | Fictional scope allowance for planning use.
Juniper Lantern Storage at Mesa Vista (Fictional) | Site Work | Drainage and paving allowance | 98000 | square feet | Draw 4 | 725000 | 690000 | 250000 |  | Fictional Site Lead | In Progress | 2026-12-10 |  |  | Review quantities and timing before use.
Juniper Lantern Storage at Mesa Vista (Fictional) | Design | Civil engineering allowance | 650 | hours | Draw 1 | 390000 | 375000 | 300000 |  | Fictional Design Team | In Progress | 2026-10-26 |  |  | Hours are fictional and editable.

## Assumptions
Development Budget Assumptions
Yellow cells are editable planning assumptions and stable validation lists. Update them for the fictional project before relying on workbook results.
Budget Limit | Editable Value | Category | Unit | Draw Period | Owner | Status
Large line review threshold | 5000000 | Land | lump sum | Predevelopment | Fictional Development Lead | Planned
Maximum amount entry | 25000000 | Design | square feet | Draw 1 | Fictional Design Team | Quoted
Earliest allowed due date | 2026-01-01 | Permits & Fees | units | Draw 2 | Fictional Project Manager | Scheduled
Latest allowed due date | 2030-12-31 | Site Work | months | Draw 3 | Fictional Finance Review | In Progress
Maximum quantity entry | 500000 | Structures | hours | Draw 4 | Fictional Site Lead | Complete
|  | Security Systems |  | Draw 5 |  | Deferred
Planning note | Keep the review threshold at or below the maximum amount entry. All examples and roles are fictional. | Contingency |  | Draw 6
|  | Other |  | Draw 7
Draw 8
Draw 9
Draw 10
Draw 11
Draw 12